## Sheet1
Team | Ovidiu-mihai | Mocanu | 5135
| Nathan | Holzworth | 5135
Part | Part | Type | Points | Milestone | Duration | Milestone Start | Milestone Due | Milestone Type | Grade | Notes
1 | Git and Coding Style | Code | 10 | [5 empty] | 10
2 | Proposal | Written | 5 | 1 | 7 | 2019-03-15 | 2019-03-22 | deliverable #1 ( part 2) | 5
3 | Core Engine | Code | 25 | 2 | 14 | 2019-03-22 | - | internal goal | 18.75
4 | Video Report #1 | Video & Written | 2 | (2) | 14 | - | 2019-04-05 | deliverable #2 (part 4) | 2 | complete
5 | Feature 1 | Code | 23 | 3 | 10 | 2019-04-05 | - | internal goal | 5.75 | no code commited, but some research done on collision detection
6 | Video Report #2 | Video & Written | 2 | (3) | 10 | - | 2019-04-15 | deliverable #3 (part 6) | 0 | not done
7 | Feature 2 | Code | 23 | 4 | 10 | 2019-04-15 | 2019-04-25 | internal goal | 5.75 | no code commited, but some research done bill boarding for particles
8 | Integration/Debugging | Code | 5 | 5 | 4 | 2019-04-25 | - | - | 2.5 | separate branches remained with entire result
9 | Report | Written | 5 | (5) | 4 | - | 2019-04-29 | deliverable #5 (parts 3,5,7,8,9) | 5
[8 empty] | Total | 44.75
-the document is obviously still in a draft state in several areas, but I'll let that be for now.
-make sure your final report is a final draft.
-FR1 some class based code, most drawing still done in using direct OGL calles in main routine
-FR2 some class abstraction, most camera manipulation done using direct OGL calls in main routine
-FR3 complete . Used third-party file parser, converted between data structures
-FR4 very partial attempt at implementing s.g. structure
-FR5 no s.g. loading, just per model loading
-FR6 not attempted
-FR7 no class abstraction, lighting still mostly direct OGL calls
-FR9 attempt and partial success in separate git branch
-FR10 not attempted