## Sheet1
Team | Ovidiu-mihai | Mocanu | 5135
| Nathan | Holzworth | 5135
Part | Part | Type | Points | Milestone | Duration | Milestone Start | Milestone Due | Milestone Type | Grade | Notes
1 | Git and Coding Style | Code | 10
2 | Proposal | Written | 5 | 1 | 7 | 2019-03-15 | 2019-03-22 | deliverable #1 ( part 2) | 5
3 | Core Engine | Code | 25 | 2 | 14 | 2019-03-22 | - | internal goal
4 | Video Report #1 | Video & Written | 2 | (2) | 14 | - | 2019-04-05 | deliverable #2 (part 4)
5 | Feature 1 | Code | 23 | 3 | 10 | 2019-04-05 | - | internal goal
6 | Video Report #2 | Video & Written | 2 | (3) | 10 | - | 2019-04-15 | deliverable #3 (part 6)
7 | Feature 2 | Code | 23 | 4 | 10 | 2019-04-15 | 2019-04-25 | internal goal
8 | Integration/Debugging | Code | 5 | 5 | 4 | 2019-04-25 | - | -
9 | Report | Written | 5 | (5) | 4 | - | 2019-04-29 | deliverable #5 (parts 3,5,7,8,9)
[8 empty] | Total | 5
-the document is obviously still in a draft state in several areas, but I'll let that be for now.
-make sure your final report is a final draft.